## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-02-25 | Deep | P2 | Open | Deep | Player is able to jump multiple times in the air | Player should only be able to jump once | Player is able to jump multiple times in the air | Press UP key multiple times
2 | 2024-02-25 | Deep | P5 | Closed | N/A | Scorpion should follow player | Scorpion should always follow or move towards the main character | Scorpion always moves left | Jump over the scorpion and then move to the right of it
3 | 2024-02-25 | Deep | P5 | Closed | N/A | Boss should follow player | Boss should always follow or move towards the main character | Boss always moves left | Jump over the Boss and then move to the right of it
4 | 2024-03-05 | Manvinder | P2 | Closed | Daman | Background moves upon rock collision | Background should not move upon rock collision | Background moves upon rock collision | Move into rock
5 | 2024-03-05 | Manvinder | P2 | Closed | Daman | Scorpions face the other way when following the player and collide into rock | Scorpion should face the player after rock collision | Scorpions face the other way when following the player and collide into rock | Jump on rock and have scorpion collide
6 | 2024-03-05 | Manvinder | P2 | Closed | Daman | Enemy keeps moving if immediately killed upon spawn | Enemy should always stop moving once killed | Enemy keeps moving if immediately killed upon spawn | Spam spacebar
7 | 2024-03-23 | Deep | P2 | Closed | Daman | Scorpion can still kill after death | Scorpions should not be able to kill after death | Scorpion can still kill after death | Kill scorpion and then collide with it
8 | 2024-03-23 | Deep | P2 | Closed | Daman | Bullet lags when shooting | Bullets should not lag when shooting. | Bullet lags when shooting | Press SPACE bar multiple times
9 | 2024-03-25 | Daman | P3 | Open | N/A | Rocks spawn too close, can't kill enemies b/w them | Rocks should spawn farther apart | Rocks spawn too close to kill any enemies inside | Run around or restart game until you find 2 rocks that are too close, with an enemy b/w them

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release